## Hoja1
Task | Member | Expected hours | Hours
Take level 1, 2 and 3 maps sprites | Adrià Martín | 5 | 4
Take level 1, 2 and 3 enemies sprites | Adrià Martín | 15 | 17
Count enemies hits (levels 1,2 and 3) | Sergi Pérez | 5 | 5.5 | Member | Total hours
Interface information and sprites | Iban Mas | 5 | 7 | Adrià Martín | 63
Original machine especifications information | Oriol Rodríguez | 5 | 5 | Sergi Pérez | 45
Put maps with debug camera | Iban Mas | 4 | 3 | Iban Mas | 69.5
Add player (without animations) | Iban Mas | 3 | 2 | Oriol Rodríguez | 39
Limit player movement to camera view | Sergi Pérez | 2 | 1.5
Move camera whit player move | Sergi Pérez | 1 | 1
Add collisions to levels 1,2 and 3 | Adrià Martín | 8 | 9
Add player animations | Adrià Martín | 5 | 4
Add laser and multilaser | Iban Mas | 6 | 10
Create title screen | Sergi Pérez | 2 | 2
Create gameover screen | Adrià Martín | 2 | 1
Create top scores screen | Oriol Rodríguez | 2 | 1
Create enter name screen | Oriol Rodríguez | 2 | 1
Create UI | Oriol Rodríguez | 5 | 5
Create basic enemy | Iban Mas | 5 | 6
Create small turret | Iban Mas | 3 | 3
Create big turret | Adrià Martín | 3 | 4
Add floor efects (lights) | Sergi Pérez | 4 | 6
Update scores | Oriol Rodríguez | 8 | 10
Title screen letters | Sergi Pérez | 5 | 8
Title screen letters | Oriol Rodríguez | 0 | 2
Teleport feature | Iban Mas | 1 | 0.5
Player collision | Oriol Rodríguez | 3 | 4
Take level 4 map sprites | Adrià Martín | 7 | 8
Take level 4 enemies sprites | Adrià Martín | 5 | 6
Change levels 1, 2 and 3 for level 4 | Iban Mas | 5 | 8
Add collisions to level 4 | Iban Mas | 4 | 5
Level 4 basic unit | Sergi Pérez | 3 | 5
Level 4 turret | Iban Mas | 2 | 3
Level 4 missile throwing enemy | Iban Mas | 3 | 4
Level 4 Boss | Iban Mas | 5 | 8
Level 4 roomba enemy | Iban Mas | 3 | 2
Level 4 train | Adrià Martín | 7 | 10
Level 4 plataforms | Sergi Pérez | 4 | 7
Power ups (Speed, shield, extend energy) | Oriol Rodríguez | 6 | 7
Power up and extra bomb | Oriol Rodríguez | 3 | 4
Ajust sound lenght | Iban Mas | 2 | 2
Module Audio | Iban Mas | 5 | 6
Take level 4 enemies sprites | Sergi Pérez | 3 | 5
Level 4 collisions | Sergi Pérez | 3 | 4
|  | 179 | 216.5